## SG safety track
Customer |  | Site. Take plan | [7 empty] | Contact. Killowen Darren O'Hare Mob: 07764 967979
Killowen Contracts |  | Laurelhill House 1A Ballymacash Park Lisburn BT28 3EX | [7 empty] | Gylnis Ellison |  |  | Tel. 07712 550723
Track Type | Spec | Location | Fitting Price | Price Uplift | Option List | Quantity | Width | Draw | Control side | Control Drop | Brackets | Fixing | Cord Tensioner | Floor to track approx | Man power | Fitting | Special Instructions
Phase 1 rooms complete ready for curtains Phase 2 rooms just started to be stripped out 03/03/26
Standard tracks as per Darren and Glynis safety or anti ligiture not required in this home
Phase 1
Ground floor
SG1080 White |  | Bedroom Door no G-030 |  |  |  | 1 | 1475 | Bi part |  |  | 3630 | Face |  | 2180 | 1 Man | 1 Man 30min | Face fix top of brackets 100mm above head D&P track overlapping reveal 150mm each side
SG1080 White |  | Bedroom Door no G-028 |  |  |  | 1 | 1480 | Bi part |  |  | 3630 | Face |  | 2185 | 1 Man | 1 Man 30min | Face fix top of brackets 100mm above head D&P track overlapping reveal 150mm each side
SG1080 White |  | Bedroom Door no G-027 |  |  |  | 1 | 1480 | Bi part |  |  | 3630 | Face |  | 2185 | 1 Man | 1 Man 30min | Face fix top of brackets 100mm above head D&P track overlapping reveal 150mm each side
SG1080 White |  | Dining Room 01.00.025 LR1 |  |  |  | 1 | 2775 | Bi part |  |  | 3630 | Face |  | 2185 | 1 Man | 1 Man 30min | Face fix top of brackets 100mm above head D&P track overlapping reveal 200mm each side
SG1080 White |  | Dining Room 01.00.025 LR2 |  |  |  | 1 | 1475 | Bi part |  |  | 3630 | Face |  | 2190 | 1 Man | 1 Man 30min | Face fix top of brackets 100mm above head D&P track overlapping reveal 150mm each side
Parking and access 0.5hr per visit
Fitting Instructions
See special instructions column for fitting detail
Small steps
Date
Key
A
B
C
D
E
F
G
H
I
J
SG 3735 spring loaded
F3A | [10 empty] | free type |  | NOTENSION |  |  | NOFITTING | Free type
IMS89