## Tracks
Customer |  | Site. See plan phase 2.4 | [7 empty] | Contact.
Bell Contracts & Co Ltd |  | Bangor Health Centre Newtownards Road Bangor Bangor BT20 4LD | [7 empty] | Project Manager Aiden Ferguson |  |  |  |  | Tel: Mob: 07731 529191
Track Type | Spec | Location | Fitting Price | Price Uplift | Option List | Quantity | Width | Draw | Control side | Control Drop | Brackets | Fixing | Hanger rods | Floor to bottom of track profile | Floor to timber joists | Floor to plaster board head | Floor to false ceiling | Floor to concrete ceiling | Man power | Fitting | Special Instructions
Phase 2.4
Ground Floor
SG 6100 Silver preformed notched for disposable curtains |  | 01.00.012 |  |  |  | 1 | [6 empty] | Using 50mm 6188 Ceiling surport bulbs WHITE OK | 2100 | 2400 |  | 2250 |  | 2 Men | 1.5hr | See plan phase 2.4
SG 6100 Silver preformed notched for disposable curtains |  | 01.00.017 |  |  |  | 1 | [6 empty] | Using 50mm 6188 Ceiling surport bulbs WHITE OK | 2100 | 2400 |  | 2250 |  | 2 Men | 1.5hr | See plan phase 2.4
SG 6100 Silver preformed notched for disposable curtains |  | 01.00.020 |  |  |  | 1 | [6 empty] | Using 50mm 6188 Ceiling surport bulbs WHITE OK | 2100 | 2400 |  | 2250 |  | 2 Men | 1.5hr | See plan phase 2.4
SG 6100 Silver preformed notched for disposable curtains |  | 01.00.022 |  |  |  | 1 | [6 empty] | Using 50mm 6188 Ceiling surport bulbs WHITE OK | 2100 | 2400 |  | 2250 |  | 2 Men | 1.5hr | See plan phase 2.4
SG 6100 Silver preformed notched for disposable curtains |  | 01.00.023 |  |  |  | 1 | [6 empty] | Using 50mm 6188 Ceiling surport bulbs WHITE OK | 2100 | 2400 |  | 2250 |  | 2 Men | 1.5hr | See plan phase 2.4
Parking and access 0.5hr
Fitting Instructions
Small steps
Date
Key
A
B
C
D
E
F
G
H
I
J
SG 3735 spring loaded
F3A | [10 empty] | free type |  | NOTENSION | [6 empty] | NOFITTING | Free type
IMS89