## SG6100
Customer |  |  | Site. See plans | [6 empty] | Contact
Felix O'Hare |  |  | Strangford Integrated College Abbey Road Carrowdore Newtownards BT22 2GB | [6 empty] | Site Manager Kevin Forsythe | [5 empty] | Telephone. ext Mob: 07917 519097
Track Type | Plan | Location | Fitting Price | Price Uplift | Option List | Quantity | Width | Draw | Control side | Control Drop | Brackets | Fixing | Bottom of track to floor height | Floor to hanger fixing heights | Floor to top of track bracket height | Floor to false ceiling height | Floor to secure grounds to be installed by others | Floor to plasterboard ceiling height | Floor to concrete ceiling height | Access equipment | Man power | Fitting | Special Instructions
Level 00
SG 6100 Silver preformed with SG6094 roller glider with hooks | Plan A & H | Room 0.110 Manufacturing Room |  |  |  | 1 | 5050 | Bi-part |  |  |  |  | Approx 2420mm |  |  |  |  | 2800 |  | L2 steps | 2 Men | 1.5hr | Fit track so bottom of curtains are 20mm from floor level
Parking & access 0.5hr
Level 00
SG 6100 White preformed with SG6147 gliders | Plan A & F | Room 0.044 Hygiene Room |  |  |  | 1 | 1300 | RH |  |  | 6503a |  |  |  | 2285 |  |  |  |  | Small steps | 1 Man | 1 Man 0.5hr | Face fix to top of timber architrave
Level 00
SG 6100 White preformed Cyclorama with SG6283 Roller gliders | Plan A & D | 0.051 Drama room Cyclorama |  |  |  | 1 | 18020 | Multi |  |  |  |  | 3000mm | 4100 to 5150 | [5 empty] | T Sgl 3.5 Mtr tower + L2, L3, L4 steps | 3 Men | 9hr | Height plus fixings confirmed with Kevin no false ceiling going in
Parking, access, tower 2hrs
Fitting Instructions
Date
Key
A
B
C
D
E
F
G
H
I
J
SG 3735 spring loaded
F3A | [10 empty] | free type |  | NOTENSION | [8 empty] | NOFITTING | Free type
IMS89