## roller
Customer |  | Site. See plans x 3 Car park facing AC Hotel barrier code 6930 Grahams entrance lagan river side of building and site offces on the first floor | [10 empty] | Contact. Project Manager Michael O'Boyle Site Manager Johnathan Jenkins & Peter McBride
John Graham Construction Ltd |  | City Quays 3 Donegal Quay Belfast BT1 3BG | [10 empty] | Site Manager Adrian McCart |  |  | Tel: Mob: Adrian 07880 406111 Michael Mob: 07385 963646
Blind Type | Plan | Measure To | Fabric Code | Width | Drop | Location | Quantity | Control Drop | Blind installation height to floor | Type of Roller | Controls | Allowance made | Control end colour | Brackets | Bracket colour | Bottom Finish | Cord Tensioner | Coil | Chain | Man power | Fitting | Special Instructions
Pink indicates DON’T MAKE BLINDS recess size with two 18mm depth skirting boards
Purple indicates DON’T MAKE BLINDS recess size with one 18mm skirting board
Level 06
Belfast Harbour Commissioners facing side
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 770 | 2640 | Stairs LR1 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Blind | Roe 3% White | 1500 | 2640 | Stairs LR2 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1273 | 2640 | Stairs LR3 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1117 | 2640 | Stairs LR4 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1080 | 2640 | LR5 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1195 | 2640 | LR6 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1266 | 2640 | LR7 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Blind | Roe 3% White | 1497 | 2640 | LR8 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 775 | 2640 | LR9 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
City Quays 2 facing side
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 770 | 2640 | LR10 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1495 | 2640 | LR11 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1145 | 2640 | LR12 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Open plan office
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1130 | 2640 | LR13 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR14 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR15 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1144 | 2640 | LR16 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1140 | 2640 | LR17 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR18 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR19 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1150 | 2640 | LR20 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1137 | 2640 | LR21 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1498 | 2640 | LR22 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1498 | 2640 | LR23 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1149 | 2640 | LR24 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1139 | 2640 | LR25 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR26 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR27 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1154 | 2640 | LR28 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1142 | 2640 | LR29 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR30 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR31 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1149 | 2640 | LR32 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1141 | 2640 | LR33 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR34 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR35 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1148 | 2640 | LR36 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1141 | 2640 | LR37 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR38 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR39 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-40 sidewinder | Plan A | Recess | Roe 3% White | 1134 | 2640 | LR40 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1147 | 2640 | LR41 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR42 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 765 | 2640 | LR43 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
The Lagan facing side
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 760 | 2640 | LR44 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1434 | 2640 | LR45 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1190 | 2640 | LR46 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1118 | 2640 | LR47 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1070 | 2640 | LR48 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1192 | 2640 | LR49 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1159 | 2640 | LR50 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR51 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 762 | 2640 | LR52 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 645 | 2640 | LR53 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1400 | 2640 | LR54 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR55 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR56 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1405 | 2640 | LR57 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1472 | 2640 | LR58 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan A | Recess | Roe 3% White | 1902 | 2640 | LR59 corner | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1260 | 2640 | LR60 corner | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR61 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR62 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1497 | 2640 | LR63 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1430 | 2640 | LR64 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1425 | 2640 | LR65 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1430 | 2640 | LR66 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Roe 3% White
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1430 | 2640 | LR67 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1265 | 2640 | LR68 corner | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
AC Hotel facing side
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1171 | 2640 | LR69 corner | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR70 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1428 | 2640 | LR71 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Open plan Office
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1425 | 2640 | LR72 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR73 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR74 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR75 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan A | Recess | Roe 3% White | 2110 | 2640 | LR76 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan A | Recess | Roe 3% White | 2670 | 2640 | LR77 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1134 | 2640 | LR78 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1498 | 2640 | LR79 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR80 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1143 | 2640 | LR81 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1132 | 2640 | LR82 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1498 | 2640 | LR83 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR84 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1142 | 2640 | LR85 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1135 | 2640 | LR86 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1498 | 2640 | LR87 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR88 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1144 | 2640 | LR89 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1135 | 2640 | LR90 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR91 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR92 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1144 | 2640 | LR93 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1134 | 2640 | LR94 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR95 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1500 | 2640 | LR96 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1147 | 2640 | LR97 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1139 | 2640 | LR98 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1496 | 2640 | LR99 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 768 | 2640 | LR100 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Belfast Harbour Commissioners facing side
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 762 | 2640 | LR101 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1496 | 2640 | LR102 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1272 | 2640 | LR103 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Roe 3% White
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1185 | 2640 | LR104 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1150 | 2640 | LR105 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1200 | 2640 | LR106 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Roe 3% White
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1261 | 2640 | LR107 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR108 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 761 | 2640 | LR109 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 685 | 2640 | LR110 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Corridor
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1469 | 2640 | LR111 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR112 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | blind | Roe 3% White | 1499 | 2640 | LR113 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 1473 | 2640 | LR114 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan A | Recess | Roe 3% White | 718 | 2640 | LR115 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
0.5hr access and parking
Customer |  | Site. See plans x 3 Car park facing AC Hotel barrier code 6930 Grahams entrance lagan river side of building and site offces on the first floor | [10 empty] | Contact. Project Manager Michael O'Boyle Site Manager Johnathan Jenkins & Peter McBride
John Graham Construction Ltd |  | City Quays 3 Donegal Quay Belfast BT1 3BG | [10 empty] | Site Manager Adrian McCart |  |  | Tel: Mob: Adrian 07880 406111 Michael Mob: 07385 963646
Blind Type | Plan | Measure To | Fabric Code | Width | Drop | Location | Quantity | Control Drop | Blind installation height to floor | Type of Roller | Controls | Allowance made | Control end colour | Brackets | Bracket colour | Bottom Finish | Cord Tensioner | Coil | Chain | Man power | Fitting | Special Instructions
Pink indicates DON’T MAKE BLINDS recess size with two 18mm depth skirting boards
Purple indicates DON’T MAKE BLINDS recess size with one 18mm skirting board
Level 05
Belfast Harbour Commissioners facing side
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 770 | 2640 | Stairs LR1 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Blind | Roe 3% White | 1500 | 2640 | Stairs LR2 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1270 | 2640 | Stairs LR3 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1113 | 2640 | Stairs LR4 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1075 | 2640 | LR5 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1198 | 2640 | LR6 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1261 | 2640 | LR7 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Blind | Roe 3% White | 1497 | 2640 | LR8 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 778 | 2640 | LR9 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
City Quays 2 facing side
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 763 | 2640 | LR10 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR11 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1144 | 2640 | LR12 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Open plan office
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1139 | 2640 | LR13 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR14 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR15 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1147 | 2640 | LR16 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1139 | 2640 | LR17 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR18 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR19 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1140 | 2640 | LR20 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1142 | 2640 | LR21 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR22 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR23 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1143 | 2640 | LR24 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1144 | 2640 | LR25 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1498 | 2640 | LR26 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR27 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1146 | 2640 | LR28 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1140 | 2640 | LR29 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR30 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR31 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1140 | 2640 | LR32 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1135 | 2640 | LR33 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR34 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR35 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1144 | 2640 | LR36 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1138 | 2640 | LR37 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR38 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR39 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1143 | 2640 | LR40 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1132 | 2640 | LR41 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR42 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 764 | 2640 | LR43 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
The Lagan facing side
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 760 | 2640 | LR44 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR45 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1274 | 2640 | LR46 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1190 | 2640 | LR47 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1151 | 2640 | LR48 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1128 | 2640 | LR49 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1268 | 2640 | LR50 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR51 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 769 | 2640 | LR52 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 715 | 2640 | LR53 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1467 | 2640 | LR54 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR55 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR56 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1475 | 2640 | LR57 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1488 | 2640 | LR58 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan B | Recess | Roe 3% White | 1902 | 2640 | LR59 corner | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1260 | 2640 | LR60 corner | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1435 | 2640 | LR61 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1425 | 2640 | LR62 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1433 | 2640 | LR63 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1425 | 2640 | LR64 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1430 | 2640 | LR65 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1425 | 2640 | LR66 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1498 | 2640 | LR67 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1264 | 2640 | LR68 corner | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
AC Hotel facing side
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1168 | 2640 | LR69 corner | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR70 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1434 | 2640 | LR71 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Open plan Office
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1428 | 2640 | LR72 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR73 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1500 | 2640 | LR74 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR75 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan B | Recess | Roe 3% White | 2114 | 2640 | LR76 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20-45 with gear assist sidewinder | Plan B | Recess | Roe 3% White | 2678 | 2640 | LR77 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1133 | 2640 | LR78 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR79 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR80 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1145 | 2640 | LR81 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1132 | 2640 | LR82 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR83 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR84 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1140 | 2640 | LR85 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1136 | 2640 | LR86 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR87 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR88 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1147 | 2640 | LR89 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1132 | 2640 | LR90 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1498 | 2640 | LR91 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1498 | 2640 | LR92 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1145 | 2640 | LR93 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1134 | 2640 | LR94 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR95 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1502 | 2640 | LR96 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1150 | 2640 | LR97 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1130 | 2640 | LR98 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR99 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 769 | 2640 | LR100 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Belfast Harbour Commissioners facing side
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 762 | 2640 | LR101 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1496 | 2640 | LR102 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1198 | 2640 | LR103 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1192 | 2640 | LR104 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1150 | 2640 | LR105 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1185 | 2640 | LR106 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1197 | 2640 | LR107 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR108 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 764 | 2640 | LR109 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 713 | 2640 | LR110 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Corridor
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1463 | 2640 | LR111 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1498 | 2640 | LR112 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | blind | Roe 3% White | 1499 | 2640 | LR113 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 1467 | 2640 | LR114 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
Defiant R20 sidewinder | Plan B | Recess | Roe 3% White | 710 | 2640 | LR115 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Fit back of brackets 90mm from window frame through two sheets of plasterboard to steel take 50mm and 70mm self tappers
0.5hr access and parking
Customer |  | Site. See plans x 3 Car park facing AC Hotel barrier code 6930 Grahams entrance lagan river side of building and site offces on the first floor | [10 empty] | Contact. Project Manager Michael O'Boyle Site Manager Johnathan Jenkins & Peter McBride
John Graham Construction Ltd |  | City Quays 3 Donegal Quay Belfast BT1 3BG | [10 empty] | Site Manager Adrian McCart |  |  | Tel: Mob: Adrian 07880 406111 Michael Mob: 07385 963646
Blind Type | Plan | Measure To | Fabric Code | Width | Drop | Location | Quantity | Control Drop | Blind installation height to floor | Type of Roller | Controls | Allowance made | Control end colour | Brackets | Bracket colour | Bottom Finish | Cord Tensioner | Coil | Chain | Man power | Fitting | Special Instructions
Pink indicates DON’T MAKE BLINDS recess size with two 18mm depth skirting boards
Purple indicates DON’T MAKE BLINDS recess size with one 18mm skirting board
Level 04
Belfast Harbour Commissioners facing side
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 770 | 2640 | Stairs LR1 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1500 | 2640 | Stairs LR2 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1500 | 2640 | Stairs LR3 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1500 | 2640 | Stairs LR4 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
White aluminium bottom bar
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1100 | 2640 | LR5 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1189 | 2640 | LR6 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1264 | 2640 | LR7 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR8 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 777 | 2640 | LR9 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
City Quays 2 facing side
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 780 | 2640 | LR10 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1498 | 2640 | LR11 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1142 | 2640 | LR12 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Open plan office
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1142 | 2640 | LR13 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR14 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR15 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1148 | 2640 | LR16 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1140 | 2640 | LR17 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR18 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR19 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1143 | 2640 | LR20 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1135 | 2640 | LR21 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR22 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR23 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1143 | 2640 | LR24 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1136 | 2640 | LR25 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1498 | 2640 | LR26 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1498 | 2640 | LR27 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1142 | 2640 | LR28 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1137 | 2640 | LR29 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR30 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR31 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1144 | 2640 | LR32 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1137 | 2640 | LR33 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR34 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR35 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1146 | 2640 | LR36 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1135 | 2640 | LR37 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR38 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR39 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1155 | 2640 | LR40 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1170 | 2640 | LR41 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1498 | 2640 | LR42 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 768 | 2640 | LR43 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
The Lagan facing side
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 760 | 2640 | LR44 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1427 | 2640 | LR45 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1215 | 2640 | LR46 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1130 | 2640 | LR47 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1115 | 2640 | LR48 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1196 | 2640 | LR49 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 1269 | 2640 | LR50 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | blind | Roe 3% White | 1499 | 2640 | LR51 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Recess | Roe 3% White | 768 | 2640 | LR52 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 760 | 2640 | LR53 | 1 | 1120 | 2640 | Chain | LH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1505 | 2640 | LR54 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1415 | 2640 | LR55 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Belfast Harbour Commissioners facing side corridor
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1499 | 2640 | LR56 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 1480 | 2640 | LR57 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Defiant R20 sidewinder | Plan C | Approx. | Roe 3% White | 700 | 2640 | LR58 | 1 | 1120 | 2640 | Chain | RH |  | White | Top | White | White aluminium bottom bar | Self adhesive plastic P Clips | Std | Metal | 1 Man | 20 min | Top fix inside 100mm wide aluminium soffit back of brackets 25mm from back of soffit
Fitting Instructions
See special instructions column
Blinds with bearing end at reveals bring brackets in 10mm from wall Blinds with control units stopping at reveals bring brackets in 5mm from walls to allow cloths to clear skirting boards to be installed
Safety devices stuck on to alum frames screw to plasterboard walls if required
Date |  | fitter | work done
Key
A |  | Blind Type Code
B |  | Measure To
C |  | Fabric code
D |  | Width
E |  | Drop | E
F |  | Location
G |  | Not required
H |  | Not required
I |  | Option codes (separated by semi colons)
J |  | Quantity (if left blank, 1 will be assumed)
[21 empty] | NOFITTING | Free type