## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Kestrel K9500 track
| Table 1 | Kestrel K9500 track
Kestrel K9500 track
| Table 1 | Kestrel K9500 track

## Kestrel K9500 track
Customer |  | Site. 1 Man work OK if fitting between 0900 to 1630hrs as Chidren will be away or at School as per Monica | [10 empty] | Contact.
SHSCT |  | Greenhill YMCA Donard Park Newcastle BT33 0GR | [10 empty] | Monica Rogan |  | Tel: Mob: 07773 135639
Track Type | Spec | Location | Fitting Price | Price Uplift | Option List | Quantity | Width | Draw | Control side | Control Drop | Gliders White or White & Grey or Grey | Extra Componnets | Fixing | Floor to track Approx | Cord Tensioner | Man power | Fitting | Special Instructions
Monica Rogan has taken photos of Panaz Spectrum and Dart cards colour TBC
Chalet 5
Ground floor
Kestrel K9500 track |  | Lounge |  |  |  | 1 | 3660 | Bi-part |  |  |  |  | Face | 2865 |  | 1 Man | 1.5hr | Face fix through plasterboard top of face fix magnets 2865mm from floor level remove old pole
Kestrel K9500 track |  | Front door |  |  |  | 1 | 850 | RH |  |  |  |  | Face | 1960 |  | 1 Man | 0.5hr | Face fix top of face fix magnets 1960mm from floor level fix directly to timber door
Kestrel K9500 track |  | Front Bedroom LR1 |  |  |  | 1 | 980 | Bi-part |  |  |  |  | Face | 2275 |  | 1 Man | 0.75hr | Face fix through plasterboard top of face fix magnets 185mm above head remove old pole
Kestrel K9500 track |  | Front Bedroom LR2 |  |  |  | 1 | 985 | Bi-part |  |  |  |  | Face | 2275 |  | 1 Man | 0.75hr | Face fix through plasterboard top of face fix magnets 185mm above head remove old pole
Kestrel K9500 track |  | Back Bedroom |  |  |  | 1 | 1780 | Bi-part |  |  |  |  | Face | 2265 |  | 1 Man | 0.75hr | Face fix through plasterboard top of face fix magnets 185mm above head remove old pole
Kestrel K9500 track |  | Office |  |  |  | 1 | 1780 | Bi-part |  |  |  |  | Face | 2270 |  | 1 Man | 0.75hr | Face fix through plasterboard top of face fix magnets 185mm above head remove old pole
parking and access 0.5hr
Fitting Instructions
L2 steps
Childrens unit Children to be at School while work being carried one Man ok to carry out work
See special instructions column for fixing detail
Kestrel K9500 track. Top of face fix magnet to glider hook 115mm. Top of top fix magnet to glider hook 65mm. Track profile to glider hook 42mm. If CP3 tape Bottom pocket nil heading
Trust spec track Kestrel K6200 track. Top of face fix magnet to glider hook 95mm. Top of top fix magnet to glider hook 45mm. Track profile to glider hook 30mm. If CP3 tape Middle pocket nil heading
Non magnetic Kestrel K2500 track. Face fix top of end brackets to glider hook 60mm. Top of profile to glider hook 40mm. If CP3 tape Top pocket nil heading
Date
Key
A
B
C
D
E
F
G
H
I
J
SG 3735 spring loaded
F3A | [11 empty] | free type |  |  | NOTENSION |  | NOFITTING | Free type
IMS89