## Sheet1
ITEM ID | ID | Department | Work Items | Status | Testing Team | Testing Start Date | Testing End Date | Going Live Date
101301000002252115 | TIP-I37 | Testing | LA-I647-Application Setup:Time Zone-Based Date and Time Format Change (45722 - Final Touch Blinds) 63247 AUS Harmony blinds(TIP-I37) | Feature in progress | Suganya, Srinivasan, Aarthi | 2025-07-02 | 2025-11-11 | 2025-11-13
101301000003395679 | TIP-I2304 | Testing | LA-I1832-(42409) Dalekit-Price Table from BOM | Feature in progress | Mahalakshmi | 2025-08-13 | 2025-10-21 | 2025-10-23
101301000003606587 | TIP-I2460 | Testing | LA-I2070–No Tax for Delivery and Fitting Costs (Leamington, Shadewell)(48445,44376) | Feature in progress | Nagaraj | 2025-05-15 | 2025-10-01 | 2025-10-14
101301000003793615 | TIP-I2455 | Testing | LA-I2272–Pricing Based on Quantity for Option-Rollerdor | Feature in progress | Arun Karthick | 2025-09-02 | 2025-09-30 | 2025-10-09
101301000003805793 | TIP-I1859 | Testing | LA-I3404 ¦ I3021 ¦ (64610) Converting account type - Umbra/Rainbow/CP(LA-I3524) | Feature in progress | Yogeshwari | 2025-08-06 | 2025-10-07 | 2025-10-17
101301000004123385 | TIP-I2543 | Testing | LA-I3881-LA-I3328-VI-I384(65999)_Scot blinds_V4-Invoice & Blinds Expert-Editing Notes_for all migrated customers | Feature in progress | Manoj | 2025-07-31 | 2025-10-13 | 2025-10-15
101301000004746547 | TIP-I2790 | Testing | LA-I3954-(79872)- AUS- Townsvile/Harmony- Notification Bubble | Feature in progress | Aravind | 2025-10-01 | 2025-10-15 | 2025-10-16
101301000004746821 | TIP-I2554 | Testing | LA-I3837-(79959)- AUS TBS: Add product name column in Default view of stock level and sort them based on Alphanumerics | Feature in progress | Yogeshwari | 2025-09-29 | 2025-10-09 | 2025-10-17
101301000004796255 | TIP-I2651 | Testing | LA-I3943-REQ-I1828-Deleted appointment type has been transferred to another type | Feature in progress | Kishore N | 2025-09-16 | 2025-10-14 | 2025-10-15
101301000004842087 | TIP-I2785 | Testing | LA-I3662-User restriction re-structure | Feature in progress | Jayachandran | 2025-10-06 | 2025-11-06 | 2025-11-14
101301000004364071 | TIP-I2844 | Testing | REQ-I1648-History double shown in notes REUTHER-Created by Don | Feature in progress | Vijay E | 2025-09-26 | 2025-10-23 | 2025-10-27
| TIP-I2854 | Testing | LA-I3515-BCC Functionality Required-Concorde V4 | Feature in progress | Manoj | 2025-10-10 | 2025-10-29 | 2025-10-30
| TIP-I2860 | Testing | LA-I3285- Automation Enhancements (5 tickets) | Feature in progress | Aravind, Karthika | 2025-10-03 | 2025-11-18 | 2025-11-20
| TIP-I2861 | Testing | LA-I1388-BWS Blinds Inc.(GETSOMESHADE)-Automation based on Line item ready status(62591) | Feature in progress | Aravind | 2025-10-03 | 2025-11-18 | 2025-11-20
| TIP-I2863 | Testing | LA-I3794-REQ-I1771-Average cost for Options & Materials-Requested by TBS | Feature in progress | Karthika | 2025-09-26 | 2025-10-20 | 2025-10-23
| TIP-I2817 | Testing | LA-I4234-(81504)-Rainbow v4-Speed Improvement in Views/ Search page | Feature in progress | Karthika | 2025-10-03 | 2025-10-24 | 2025-10-26
| TIP-I2892 | Testing | LA-I4105-HomeCreations-Express Option additional including Saturday,Sunday & Holidays | Feature in progress | Mahalakshmi | 2025-10-09 | 2025-10-15 | 2025-10-16
| TIP-I2898 | Testing | LA-I4031-(81759)_Final touch blinds_V4_Accounting Transfer Contact Name | Feature in progress | Srinivasan | 2025-09-15 | 2025-10-13 | 2025-10-14
| TIP-I2942 | Testing | LA-I3670-Reuther Site Address Change Phase 2 | Feature in progress | Nithiyaraj, Suganya | 2025-09-25 | 2025-10-13 | 2025-10-23
101301000005031491 | TIP-I2839 | Testing | LA-I4016-REQ-I1890-Home creations-Bulk update requires on Subfields | Feature in progress | Harish Kumar | 2025-10-06 | 2025-10-15 | 2025-10-16
101301000005173079 | TIP-I2828 | Testing | LA-I4155-(80092)- CPINTERIORS Turnover view and the dashboard | Bugs in progress | Mahalakshmi | 2025-10-06 | 2025-10-14 | 2025-10-16
101301000005173987 | TIP-I2824 | Testing | LA-I4220-Blind Matrix-Excel Templates(82242) | Bugs in progress | Arun Karthick | 2025-10-10 | 2025-10-13 | 2025-10-14
101301000005221723 | TIP-I2819 | Testing | LA-I4218-West Coast Vertical Components: Issue with Import of ZIP Code Tax(82596) | Bugs in progress | Aravind | 2025-10-07 | 2025-10-13 | 2025-10-15
101301000004970227 | TIP-I2835 | Testing | LA-I3931-Seperate pricetable issue on the job form(LA-I3855) | Bugs in progress | Arun Karthick | 2025-10-10 | 2025-10-16 | 2025-10-17
101301000005144343 | TIP-I2834 | Testing | LA-I4108 ¦ Additional Contacts-(81467) | Bugs in progress | Suganya | 2025-09-24 | 2025-10-10 | 2025-10-13
101301000005187637 | TIP-I2830 | Testing | LA-I4156-FollowUp-Shutter Visualisation Phase 1 | Bugs in progress | Manoj | 2025-10-02 |  | 2025-10-21
| TIP-I2917 | Testing | LA-I4287-Toggle button UI changes on Job Form | Bugs in progress | Abdul Sathar, Shiva Ranjani | 2025-10-09 | 2025-10-17 | 2025-10-22
101301000005263763 | TIP-I2870 | Testing | LA-I4269-Task Screen Missing (80724)-Talbot | Bugs in progress | Vijay E | 2025-10-07 | 2025-10-09 | 2025-10-16
| TIP-I2918 | Testing | LA-I4184-Blinds Expert-Default Invoice email not fetching when sending email(82520)-TIP-I2779 | Bugs in progress | Abdul Sathar, Vijay E | 2025-10-01 | 2025-10-01 | 2025-10-15
| TIP-I2919 | Testing | RAINBOW-Emailing Invoices (81564) | Bugs in progress | Vijay E | 2025-10-01 | 2025-10-01 | 2025-10-15
| TIP-I2661 | Testing | TIP-I2661-LA-I4097-R & D for loading very slow subfield (TBS) | Bugs in progress | Kishore N | 2025-09-29 | 2025-10-07 | 2025-10-17
| TIP-I2926 | Testing | TIP-I2875 (82812) - Sienna Shutters -Dashboard not showing the correct data on Appointment Views | Bugs in progress | Jayachandran | 2025-10-10 | 2025-10-14 | 2025-10-15
101301000005123003 | TIP-I2883 | Testing | LA-I4086-TIP-I2883(79656)-RAINBOW V4-ERRORS Unable to re-transfer | Bugs priority | Yogeshwari | 2025-10-13 | 2025-10-17 | 2025-10-20
101301000005237861 | TIP-I2894 | Testing | LA-I4221-Appointment & common Bugs | Bugs priority | Karthika | 2025-10-13 | 2025-10-15 | 2025-10-16
101301000005076501 | TIP-I2902 | Testing | LA-I4030-(81580)-Reuther-Motorisation options not loading | Bugs priority | Yogeshwari | 2025-09-15 | 2025-10-15 | 2025-10-17
101301000005132667 | TIP-I2908 | Testing | LA-I4095-Invoiced jobs editable on Online portal not working based on the settings | Bugs priority | Arun Karthick | 2025-10-15 | 2025-10-16 | 2025-10-17
101301000005188291 | TIP-I2906 | Testing | TIP-I2906-(81691)-Rainbow V4-Fabric Missing on the job | Bugs priority | Yogeshwari | 2025-09-24 | 2025-10-17 | 2025-10-21
| TIP-I2921 | Testing | LA-I4290-Sequence numeric isn't working (81019) Aus Artessa | Bugs priority | Yogeshwari | 2025-10-10 | 2025-10-13 | 2025-10-15
| TIP-I2923 | Testing | LA-I4174-Online portal changes for mobile and tablet browsers | Bugs priority | Suganya | 2025-10-10 | 2025-10-14 | 2025-10-16
| TIP-I2831 | Testing | LA-I4062-CC not Listing in communication and job show more while drafting a mail | Bugs priority | Arun Karthick | 2025-09-17 | 2025-10-17 | 2025-10-21
| TIP-I2927 | Testing | TIP-I2807-(82728)-Sienna Shutters-gross override issue | Bugs priority | Suganya | 2025-10-13 | 2025-10-16 | 2025-10-21
101301000005272339 | TIP-I2914 | Testing | LA-I4283-Blinds Expert-Production Due Date not working (82838) | Bugs priority | Arun Karthick | 2025-10-10 | 2025-10-14 | 2025-10-17
| TIP-I2887 | Testing | LA-I3710¦REQ-I1692-(74160) Umbra Shading V4- Visibility on Agent Quotes/Orders in desktop | Feature Priority | Aravind
| TIP-I2837 | Testing | LA-I2878-67217-Reuther-Automation requirements(67217) | Feature Priority | Suganya
101301000005096557 | TIP-I2920 | Testing | TIP-I2796-Re:Task reminder on Desktop (81977)-Concorde | Need to duplicate bug | Arun Karthick | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005292239 | TIP-I2928 | Testing | Read Window Products LLC -Workroom App-Semi Strict (79267) | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005293387 | TIP-I2929 | Testing | TIP-I2929-(82873)-Rainbow v4-Label issue | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005295171 | TIP-I2934 | Testing | #83045- Aus- Kenlow- Email Not Verified When Client Clicks and Accepts the Quote | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005295187 | TIP-I2935 | Testing | TIP-I2935 #83021 - Product not saving V4 Dutton and Guavin DB | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005279075 | TIP-I2936 | Testing | (82899)-AUS Metro Shades-doubling up when optimising | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005292929 | TIP-I2940 | Testing | Rollerdor Ltd- stock allocation | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005294385 | TIP-I2941 | Testing | TIP-I2941 #83053 - Rework Glitch V4 Goldcrest commercial | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
101301000005294423 | TIP-I2943 | Testing | #83054 Umbrashading Re: Email Templates in Trade Portal | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
| TIP-I2622 | Testing | TIP-I2439-(81645)_Concorde_V4_FW: Deposit not showing(TB-I1456) | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
| TIP-I2619 | Testing | TIP-I2619-(81654)-AbCompany Automation-Review text | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
| TIP-I2630 | Testing | Marske Furnishings Ltd-Payment allocated in background(82278) | Need to duplicate bug | Nithiyaraj, Suganya, Arun Karthick | 2025-10-10 | 2025-10-13 | 2025-10-16
| TIP-I2600 | Testing | TIP-I2600-Marske Furnishings Ltd - Order job Status changed -UK-AJ-(82321) | Need to duplicate bug | Nithiyaraj | 2025-10-10 | 2025-10-13 | 2025-10-16
| TIP-I2769 | Testing | REQ-I1896 ¦ Fabricom -Online Portal Transalation | Testing Scenarios | Nagaraj, Rex John Paul | 2025-10-13 | 2025-10-13 | 2025-10-16
| TIP-I2699 | Testing | TIP-I2699 -(46236)_EDI Arena, Decora Priority orders (New Home Floorings) | Testing Scenarios | Rex John Paul, Nagaraj | 2025-10-03 | 2025-10-09 | 2025-10-16
| TIP-I2693 | Testing | REQ-I1880 ¦ VU Window Treatments -Email based on Alternate Delivery address | Testing Scenarios | Nagaraj, Rex John Paul | 2025-09-30 | 2025-10-07 | 2025-10-16
| TIP-I2755 | Testing | TIP-I2755-REQ-I1865 ¦ European number format - (REUTHER)- Created by Don | Testing Scenarios | Nithiyaraj | 2025-09-30 | 2025-10-07 | 2025-10-16
| TIP-I2698 | Testing | REQ-I1907 ¦ (82166)- AUS TBS: Need ability to download product-based worksheet format templates from the online portal | Testing Scenarios | Rex John Paul, Nagaraj | 2025-10-03 | 2025-10-09 | 2025-10-14
Note on D1: This is a mandatory field. Please enter appropriate values.