| Project | ETZ Scale Up Hub |
| --- | --- |
| Project No. | 3165 |

| Sub-Contractor |  |
| --- | --- |
| Name | Grampian Blinds Limited |
| Regional address | Unit 1B, Mugiemoss Road, Aberdeen, AB21 9US |
| Company Registration No. | SC232209 |
| Telephone | 01224 662 884 |
| Email | enquiries@grampian-blinds.co.uk sales@grampian-blinds.co.uk |
| Registered address (if different from above) | Unit 10 Craig Leith Road, Stirling, Scotland, FK7 7GN |
| Database status | Yes |
| Reason for status (if not approved) | n/a |
| If the Sub-Contractor is not on the OGILVIE approved database, a pre-qualification questionnaire form should be completed and returned. Until this has been approved, no order can be placed, or payments made. |  |
| Work package title | Supply, Installation of BLINDS Works on the ETZ project |
| Work package reference |  |
| Date of meeting | 23/04/2025 |
| Venue of meeting | ETZ site office |

| Present (The persons present confirm they have authority to agree matters on behalf of their company) | Ogilvie | Sub-Contractor |
| --- | --- | --- |
|  | Jamie Ireland | Steven Nimmo |
|  | Joseph Rudden |  |
|  | Ben Marshall |  |

| Minutes prepared by | Ben Marshall + Joseph Rudden |
| --- | --- |
| Distribution | All above |

| 1. Introduction |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Project description |  | Construction of a new collaboration hub and 2 nr scale up units with all associated external works, drainage and services |  |  |  |  |  |
| 1.2 | Site address |  | Hareness Road, Altens |  |  |  |  |  |
|  | Telephone number |  |  |  |  |  |  |  |
|  | Project email |  |  |  |  |  |  |  |
| 1.3 | Correspondence procedure |  | Any written notices to be delivered via recorded delivery to Ogilvie Construction Limited, Ogilvie House, 200 Glasgow Road, Stirling, FK7 8ES |  |  |  |  |  |
|  |  |  | Important note: The serving of Notices will be dealt with under the Sub-Contract Conditions. |  |  |  |  |  |
| 1.4 | Ogilvie staff involved in the project |  |  |  |  |  |  |  |
|  | Site / project staff |  |  |  |  |  |  |  |
|  | Project Manager |  | Jamie Ireland | Tel | 07442 081398 |  |  |  |
|  |  |  |  | Email | jamie.ireland@ogilvie.co.uk |  |  |  |
|  | Site Manager |  | TBC | Tel |  |  |  |  |
|  |  |  |  | Email |  |  |  |  |
|  | Building Services Manager |  | TBC | Tel |  |  |  |  |
|  |  |  |  | Email |  |  |  |  |
|  | Design Manager |  | TBC | Tel |  |  |  |  |
|  |  |  |  | Email |  |  |  |  |
|  | Quantity Surveyor |  | Benjamin Marshall | Tel | 07425334246 |  |  |  |
|  |  |  |  | Email | Benjamin.marshall@ogilvie.co.uk |  |  |  |
|  | Assistant Surveyor |  | Joseph Rudden | Tel | 07350 364707 |  |  |  |
|  |  |  |  | Email | Joseph.rudden@ogilvie.co.uk |  |  |  |
|  | Document Controller |  | TBC | Tel |  |  |  |  |
|  |  |  |  | Email |  |  |  |  |
|  | Head office staff |  |  |  |  |  |  |  |
|  | Operations Director |  | David Mason | Tel | 07551 010108 |  |  |  |
|  |  |  |  | Email | David.mason@ogilvie.co.uk |  |  |  |
|  | Commercial Manager |  | Ryan Green | Tel | 07407 899 769 |  |  |  |
|  |  |  |  | Email | ryan.green2@ogilvie.co.uk |  |  |  |
|  | Operations Manager / Project Director |  |  | Tel |  |  |  |  |
|  |  |  |  | Email |  |  |  |  |
|  | HSQ&E Manager |  | Stewart Morrison | Tel | 07753 720 352 |  |  |  |
|  |  |  |  | Email | Stewart.morrison@ogilvie.co.uk |  |  |  |
| 1.5 | Sub-Contractor staff involved in the project. This section must clearly define the sub-contractor level of management/supervision involved in the project and identify who is on/off site |  |  |  |  |  |  |
|  | Site staff |  |  |  |  |  |  |
|  | Project Manager – Full time or P/T |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | Site Manager – Full time or P/T |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | Site Supervisor, Full Time – Non-Working |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | Site Supervisor, Full Time - Working |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | O&M / completion documentation |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | HS&E Manager |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | QA Manager / Passivhaus Manager |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | Commercial Manager |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
|  | Director |  |  | Tel |  |  |  |
|  |  |  |  | Email |  |  |  |
| 1.6 | Sub-Contractor management & supervision |  |  |  |  |  |  |
|  | Site staff |  |  |  |  |  |  |
|  | - Frequency of visits by part time Manager: |  |  | Daily or as required |  |  |  |
|  | - The Sub-Contractor must keep the same supervisor/foreman and operatives on site for the duration of the Sub-Contract Works. Any operatives arriving for work without a supervisor/foreman will not be allowed to commence works. Any subsequent delays will be attributable to the Sub-Contractor. |  |  |  |  |  |  |
|  | - It is the Sub-Contractor’s managers’ responsibility to fully brief his supervisor/foreman prior to attending site, and on a regular basis thereafter, to ensure that the supervisor/foreman is fully aware of the requirements of the sub-contract, specification, drawings, interfaces etc. and can fully complete the sub-contract Works. Ogilvie management time in fulfilling this role will be charged to the Sub-Contractor if the Sub-Contractor defaults on this requirement. Ogilvie reserve the right to stop the sub-contract works if the appropriate level of management or supervision is not in place by the sub-contractor, with any delays being attributable to the Sub-Contractor. |  |  |  |  |  |  |
|  | - The onsite supervisor and visiting manager are required to attend regular progress/co-ordination meetings, as requested by Ogilvie. The Sub-Contractor is to prepare a progress report prior to these meetings, identifying both on and off-site activities and issue this report to Ogilvie relevant manager, in advance of the progress meeting. Should this report not be issued, Ogilvie reserve the right to make a deduction from the Sub-Contractor’s account, up to £250 per report not issue. |  |  |  |  |  |  |
|  | - Sub-Contractor anticipated workforce: |  |  |  |  |  |  |
|  | Own operatives: | 2 ops |  |  |  |  |  |
|  | S/C operatives: | n/a |  |  |  |  |  |
|  | Provide details of any Sub-Sub-Contracted works: | n/a |  |  |  |  |  |
|  | - Sub-Contractor to provide a detailed labour histogram prior to starting on site. Non-provision of this shall result in a deduction of £250 from the subcontract account. |  |  |  |  | Yes / No |  |
|  | - No agency labour is to be employed by the Sub-Contractor without the prior written consent from Ogilvie. |  |  |  |  |  |  |
|  | - Does the Sub-Contractor intend to employ agency labour on the project? |  |  |  |  |  | Yes / No |
|  | - Daily and weekly record of staff, labour, plant, and hours are to be submitted by the Sub-Contractor for record purposes by the Monday of the week following the works being carried out. Ogilvie also reserve the right to make a deduction from the Sub-Contractor’s account if this is not issued, up to £100 for each weekly record not submitted. |  |  |  |  |  |  |
|  | - All visitors & operatives are required to sign in and out of site daily in the sign in book. |  |  |  |  |  |  |

| 2. Analysis of Sub-Contractor’s bid (Details on which the Sub-Contractor’s bid is based) This section must be discussed in detail within this meeting to ensure all parties are fully aware of the sub-contract requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Relevant documentation |  |  |  |  |
|  | Employer requirements | Confirmation from Architect: - “The client would like to proceed with the Shading specialists Ltd “Diaz” smart chain operated roller blind in Eco friendly fabric” - “The finish should be stainless steel or aluminium mechanisms where possible, but silver or light grey plastic is a suitable alternative if not and a light grey blind fabric, please” - “The blinds are required to be face fixed to the inside face of the timber directly above the glazed screens, not within the ingo as most screens are inward opening and we don’t want a clash. I expect this is the intention anyway but best to check. - “We also expect that as some blinds are placed quite high, the chain length will be extended to remain accessible however, we expect the manufacturer to account for this and apply their knowledge to a suitable approach” - “We don’t expect all the screens require blinds at this point therefore, the client would like to proceed with a reduced scope for only essential blinds” |  |  |  |
|  | Drawings (including revision status) | As above |  |  |  |
|  | Specification (including revision status) | As above |  |  |  |
|  | Bills of Quantities |  |  |  |  |
|  | Preliminaries | Included |  |  |  |
|  | Other documents / comments | Community Benefits STA_AN4_Part 1-Foundation Tolerances-Jan 14 OCL approach to ETZ Net Zero Principles Road to Zero – Ogilvie Construction ETZ – Schedule Part 9 (iv) The Contract Drawings 22.08.24 ETZ – Schedule Part 9 (v) Employers Requirements ETZ – Main Contract info and requirements |  |  |  |
| 2.2 | Compliance with the documents / qualifications / clarifications |  |  |  |  |
|  | Is the bid fully compliant with the documents provided to the Sub-Contractor? |  | Yes / No |  |  |
|  | If ‘no’ identify where items of work are non-compliant: |  |  |  |  |
|  | Has non-compliance been formally approved by the Client and relevant Design Consultants? |  |  |  |  |
| 2.3 | Scope / interface |  |  |  |
|  | The Sub-Contractor is responsible for interface and co-ordination of their works with the following contractors: - Internal finishing trades The Sub-Contractor is responsible for any delays to their works, or others works, if this co-ordination does not occur, including any resultant commercial implications. |  |  |  |
| 2.4 | Specification / performance requirements |  |  |  |
|  | As per Main Contract |  |  |  |
| 2.5 | Sequence – builders work requirements / inclusions |  |  |  |
|  | Programme ref: As per section 5. Sequencing: As per section 5 |  |  |  |
| 2.6 | Further areas of Value Engineering |  |  |  |
|  | To be considered throughout the works. The Sub-Contractor is invited to explore any areas of value engineering that they feel may be of benefit to the Project. Under no circumstances should any changes to the Sub-Contract Works be made without the prior written approval of Ogilvie. |  |  |  |
| 2.7 | Social Value (SV) & Community Benefits (CB) (e.g. Training and / or Environmental Commitments) |  |  |  |
|  | The Sub-Contractor is responsible for the provision of the following SV and CB deliverables on this project: - N/a Ogilvie reserve the right to deduct up to £500 for non-provision of each deliverable, if not provided by the Sub-Contractor. |  |  |  |

| 3. Commercial Matters |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Terms & Conditions Any works carried out or commenced will be subject to and in accordance with the Sub-Contract. If another standard form of Sub-Contract is to be used, please indicate below: |  |  |  |  |  |  |  |  |  |  |
|  | The Sub-Contract Order shall be placed in full accordance with Ogilvie Standard Terms & Conditions which shall take precedence, in all instances, over all conditions in the Sub-contractor’s tender, as and where applicable, unless expressly agreed otherwise within the content of this document. Any requirement to amend Ogilvie Standard Terms & Conditions shall be mutually agreed between the parties and incorporated and referenced thereto within the Sub-Contract Order. |  |  |  |  |  |  |  |  |  |  |
|  | No payment will be made until the executed Sub-Contract is signed, un-amended and returned to Ogilvie. |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Description and scope of the Sub-Contract works |  |  |  |  |  |  |  |  |  |  |
|  | Supply, Installation of BLINDS Works on the ETZ project |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Sub-Contract Numbered Documents |  |  |  |  |  |  |  |  |  |  |
|  | Numbered Documents list attached and agreed? |  |  |  |  |  |  |  |  |  | Yes / No |
| 3.4 | Sub-Contract Sum |  |  |  |  |  |  |  |  |  |  |
|  | Total works |  |  |  |  |  |  |  |  |  |  |
|  | Total project sum |  |  | £10,854.68 |  |  |  |  |  |  |  |
|  | Discounts |  |  | Less 0% mcd |  |  |  |  |  |  |  |
|  |  |  |  | These are commercial discounts, not discounts for payment terms. All discounts shall be applicable to variations. |  |  |  |  |  |  |  |
| 3.5 | Quantities |  |  |  |  |  |  |  |  |  |  |
|  | Lump sum |  |  | Yes / No |  |  |  | Subject to re-measurement |  |  | Yes / No |
|  | If the order value contains a mixture of lump sum and re-measurable items, this must be clearly indicated in the Sub-Contract Sum Analysis. Price fixed for duration of subcontract works |  |  |  |  |  |  |  |  |  |  |
| 3.6 | Variations |  |  |  |  |  |  |  |  |  |  |
|  | Any variation to the Sub-Contract Sum will only be considered if accompanied by a site instruction signed by Ogilvie Project Manager and/or Project Quantity Surveyor. The Sub-Contractor is to request written instruction to expend all Provisional Sums as included within the build up to Sub-Contract Sum. For absolute clarity Ogilvie confirm that all Provisional Sums are Defined Provisional Sums and are allowed for within the Sub-Contract period to carry out the Works. Should Ogilvie not instruct expenditure of these Provisional Sums then they are to be omitted from the Sub-Contract Sum. |  |  |  |  |  |  |  |  |  |  |
| 3.7 | Interim Valuation |  |  |  |  |  |  |  |  |  |  |
|  | Valuation Periods |  |  | Monthly |  |  |  |  |  |  |  |
| 3.8 | Application for Payment |  |  |  |  |  |  |  |  |  |  |
|  | Applications for payment with all details required must be submitted in accordance with Valuation Timetable. Applications for payment must be set out in the same format as the Sub-Contract Sum Analysis (failure to submit these in this format may result in the Application being rejected). |  |  |  |  |  |  |  |  |  |  |
|  | Applications for payment must be submitted to all these email addresses: - |  |  |  |  |  | Ryan.Green2@Ogilvie.co.uk |  |  |  |  |
|  |  |  |  |  |  |  | Benjamin.marshall@ogilvie.co.uk |  |  |  |  |
|  |  |  |  |  |  |  | afp@ogilvie.co.uk |  |  |  |  |
| 3.9 | Due Dates are as follows (one monthly date or schedule of dates): |  |  |  |  |  |  |  |  |  |  |
|  | Refer to Application for Payment Schedule appended to these minutes |  |  |  |  |  |  |  |  |  |  |
| 3.10 | Payment terms: |  |  |  |  |  |  |  |  |  |  |
|  | In full accordance with Ogilvie Standard Terms & Conditions |  |  |  |  |  |  |  |  |  |  |
| 3.11 | Retentions |  |  |  |  |  |  |  |  |  |  |
|  | 3 |  | % retention to be held during the Sub-Contract Works |  |  |  |  |  |  |  |  |
|  | 1.5 |  | half release after the period stated within the Sub-Contract Particulars and following completion of Sub-Contract Works |  |  |  |  |  |  |  |  |
|  |  |  | final release the later of the period stated within the Sub-Contract Particulars following completion of Sub-Contract Works, making good of all defects and agreement of final account |  |  |  |  |  |  |  |  |
| 3.12 | Daywork rates |  |  |  |  |  |  |  |  |  |  |
|  | (a) Unskilled labour: |  |  | N/A |  |  |  |  |  |  |  |
|  | (b) Skilled labour: |  |  | N/A |  |  |  |  |  |  |  |
|  | (c) Plant: |  |  | N/A Fair and reasonable prices to be agreed |  |  |  |  |  |  |  |
|  | (d) Materials: |  |  | N/A |  |  |  |  |  |  |  |
|  | (e) NPO Rates: |  |  | N/A |  |  |  |  |  |  |  |
|  | For valuation purposes if no rates are identified above, the prime cost of daywork for labour is to be calculated in accordance with the definition prepared and published by the RICS. No work will be valued as daywork except where, in the opinion of Ogilvie, it would be unfair to value such works using any other method as provided for in within clause 17 of the Sub-Contract and the Sub-Contractor has given due notice to the nominated Ogilvie representative, specified in the Sub-Contract Particulars, who has approved it in writing prior to the Sub-Contractor commencing execution thereof. Any unsigned daywork sheets will not be considered for inclusion within the final account. |  |  |  |  |  |  |  |  |  |  |
| 3.13 | Liquidated & Ascertained Damages |  |  |  |  |  |  |  |  |  |  |
|  | £5k p/wk Capped at 10% of subcontract value |  |  |  |  |  |  |  |  |  |  |
| 3.14 | Defects liability period |  |  |  |  |  |  |  |  |  |  |
|  | 12 | months after the Date of Practical Completion of the Principal Contract Works |  |  |  |  |  |  |  |  |  |
| 3.15 | Design responsibility |  |  |  |  |  |  |  |  |  |  |
|  | By Sub-Contractor |  |  |  | Yes / No |  |  |  | By others | Yes / No |  |
|  | If the Sub-Contractor is responsible for design and it is intended to sub-let that design, Ogilvie require a Sub-Sub-Consultancy Warranty from that designer. Details of the designer: |  |  |  |  |  |  |  |  |  |  |
| 3.16 | Insurance |  |  |  |  |  |  |  |  |  |  |
|  | Employer’s Liability Insurance |  |  |  |  |  |  |  |  |  |  |
|  | Certificate issued by: |  |  |  |  |  |  |  |  |  |  |
|  | Date of certificate: |  |  |  |  |  |  |  |  |  |  |
|  | Expiry of insurance: |  |  |  |  |  |  |  |  |  |  |
|  | Cover: |  |  |  |  |  |  |  |  |  |  |
|  | Public Liability Insurance |  |  |  |  |  |  |  |  |  |  |
|  | Certificate issued by: |  |  |  |  |  |  |  |  |  |  |
|  | Date of certificate: |  |  |  |  |  |  |  |  |  |  |
|  | Expiry of insurance: |  |  |  |  |  |  |  |  |  |  |
|  | Cover: |  |  |  |  |  |  |  |  |  |  |
|  | Works Insurance (contractors all risk) |  |  |  |  |  |  |  |  |  |  |
|  | Certificate issued by: |  |  |  |  |  |  |  |  |  |  |
|  | Date of certificate: |  |  |  |  |  |  |  |  |  |  |
|  | Expiry of insurance: |  |  |  |  |  |  |  |  |  |  |
|  | Cover: |  |  |  |  |  |  |  |  |  |  |
|  | Professional Indemnity Insurance / Product Liability Insurance* (* delete as applicable) |  |  |  |  |  |  |  |  |  |  |
|  | Certificate issued by: |  |  |  |  |  |  |  |  |  |  |
|  | Date of certificate: |  |  |  |  |  |  |  |  |  |  |
|  | Expiry of insurance: |  |  |  |  |  |  |  |  |  |  |
|  | Cover: |  |  |  |  |  |  |  |  |  |  |
| 3.17 | Details of Warranties required & agreement of wording |  |  |  |  |  |  |  |  |  |  |
|  | Any comments / required amendments to the proposed wording must be notified within 3 working days of this meeting or before works commence on site whichever is the earlier. Warranties shall be signed and returned to Ogilvie in accordance with the Sub-Contract Conditions. Ogilvie are entitled to withhold all payments until the Warranties are signed and returned. |  |  |  |  |  |  |  |  |  |  |
| 3.18 | Details of bonds / PCG’s required & dates when they will be issued |  |  |  |  |  |  |  |  |  |  |
|  | n/a |  |  |  |  |  |  |  |  |  |  |

| 4. Attendances |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Item |  | by Ogilvie | by Sub-Contractor | Comments |
|  | Materials | Banksman |  |  | n/a |
|  |  | Supervision |  |  |  |
|  |  | Unload |  |  |  |
|  |  | Distribution |  |  |  |
|  |  | Hoist |  |  | n/a |
|  |  | Protection |  |  |  |
|  |  | Testing |  |  |  |
|  | Plant | Small tools |  |  |  |
|  |  | Storage |  |  |  |
|  |  | Job specific plant |  |  |  |
|  |  | Concrete pump |  |  | n/a |
|  | Lifting | Appropriate plant |  |  |  |
|  |  | Appointed person |  |  |  |
|  |  | Hoist |  |  | n/a |
|  |  | Hoist operator |  |  | n/a |
|  | Hardstanding | Provision of hardstanding |  |  | n/a |
|  |  | Checks on hardstanding |  |  | n/a |
|  | Protection | Of works |  |  |  |
|  |  | Of surrounding works |  |  |  |
|  | Cleaning | Rubbish into segregated skips |  |  |  |
|  |  | Provision of skips |  |  |  |
|  | Setting Out | Provision of external datums (per elevation) |  |  | n/a |
|  |  | Provision of internal datums (per floor) |  |  | n/a |
|  |  | Setting out of the works |  |  |  |
|  |  | Line & level check |  |  |  |
|  | Scaffold | General access |  |  |  |
|  |  | Safety netting |  |  | n/a |
|  |  | Edge protection |  |  |  |
|  |  | Access Towers / MEWP |  |  |  |
|  | BWIC | Holes 75mm Dia or Less |  |  | n/a |
|  |  | Holes more Than 75mm Dia |  |  | n/a |
|  |  | Other please specify: |  |  |  |
|  | Design | Of the works |  |  |  |
|  |  | Temporary works |  |  |  |
|  | Supervision | Of the works |  |  |  |
|  |  | Of deliveries & distribution |  |  |  |
|  | Facilities | Welfare |  |  | Kitchen, toilet, drying room |
|  |  | General storage |  |  |  |
|  |  | Office space/cabins |  |  | No office space for sub-contractor |
|  |  | Office furniture |  |  | n/a |
|  |  | Phone connection |  |  | n/a |
|  |  | Phone usage |  |  | n/a |
|  |  | Electric connection |  |  |  |
|  |  | Electric usage |  |  |  |
|  |  | Water connection |  |  |  |
|  |  | Water usage |  |  |  |
|  |  | Waste connection |  |  |  |
|  |  | Site office cleaning |  |  |  |
|  | Services | Power outlets |  |  |  |
|  |  | Extension leads |  |  |  |
|  |  | Water supply |  |  |  |
|  |  | Hose pipe |  |  |  |
|  | Lighting | Safety |  |  |  |
|  |  | Task |  |  |  |
|  | PPE | Hard hats |  |  |  |
|  |  | Safety boots |  |  |  |
|  |  | High visibility vest |  |  |  |
|  |  | Eye protection |  |  |  |
|  |  | Hand protection |  |  |  |
|  |  | Job specific PPE |  |  |  |
|  | Others | Adherence to Ogilvie Hard Hat policy |  |  |  |
|  |  | Permits to be done by Sub-Contractor |  |  |  |
|  | Whilst Ogilvie may offer the use of these facilities the Sub-Contractor acknowledges that all the facilities are shared, and their use shall be prioritised strictly by the Ogilvie’s Site Management. In the event Ogilvie are unable to make these attendances available due to circumstances outside of Ogilvie’s control, the Sub-Contract will be responsible for making alternative arrangements to progress their works. No claims from the Sub-Contractor in respect of lack of such facilities shall be entertained. |  |  |  |  |
| 4.2 | Cleaning |  |  |  |  |
|  | To ensure a safe working environment the Sub-Contractor is to instruct their operatives on site to remove their waste daily. At the end of each working day the Site Manager will inspect the site works for any waste. Should the Site Manager locate any of the Sub-Contractor’s waste, he will employ labourers to remove the Sub-Contractor’s waste on their behalf. The Site Manager will keep records of resources expended and notify the Sub-Contractor accordingly. Labour costs will be set off from the Sub-Contractor’s account, at a rate of £50 per hour in conjunction with an administration charge of £250 for each notification. Ogilvie also reserve the right to suspend the Sub-Contract works in any area(s) where cleanliness is not to Ogilvie requirements. Any delay attributed to such suspension shall be the Sub-Contractor’s responsibility, including any costs incurred because of works being suspended. If provision of skips is the Sub-Contractor’s responsibility Ogilvie will also set-off any additional costs for provision & management of those skips. |  |  |  |  |
| 4.3 | Parking on site |  |  |  |  |
|  | Parking is allowed on site unless by prior arrangement with Ogilvie. In the event arrangements are made for parking on site, Ogilvie accept no responsibility for any damage, accidental or otherwise, to any vehicles or equipment. It is the responsibility of the Sub-Contractor to ensure their vehicles, and the vehicles of their employees are covered by their own insurance while on site. |  |  |  |  |
| 4.4 | Security |  |  |  |  |
|  | The Sub-Contractor is entirely responsible for his own materials and plant on the site. Whilst site security may be employed, this is not guaranteed and, in any event, Ogilvie accepts no responsibility. |  |  |  |  |
| 4.5 | Details of Client’s security requirements / documents |  |  |  |  |
|  | Site perimeter is fenced off and CCTV set up However, Ogilvie will not assume any responsibility for any property lost or damaged on site. |  |  |  |  |

| 5. Programme |  |
| --- | --- |
| The anticipated date for the commencement of the Sub-Contract Works on site will be: | 22/09/2025 |
| The notice period for the exact commencement date: | 5 weeks |

| Phase/operation | Drawing preparation period | Drawing approval period/ latest date | Offsite fabrication/ delivery period | Material procurement / latest date | Delivery dates | Provisional start date | Site works duration | Labour & resources |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Blinds |  |  | 5 weeks to attend site, site measure and fabricate blinds |  |  | 22/09/2025 | 1 week | 2 fitters |  |
| All works mentioned above are to be started and completed in line with Main Contractors programme. |  |  |  |  | Overall duration of project works (calendar): |  | 1 week |  |  |

It is the Sub-Contractor’s responsibility to request and/or issue all necessary information, details, drawings, site dimensions and the like which will be necessary for the Sub-Contractor to complete within the above dates. The Sub-Contractor must produce such information as requested when necessary for the progress of other trades and the Main Contractor’s programme.

| 5.1 | Site working hours: (subject to Planning Restrictions) |  |
| --- | --- | --- |
|  | Monday to Thursday | 07:30am – 05:00 pm |
|  | Friday | 07:30am – 3:30 pm |
|  | Saturday | 07:30am – 13:00 pm (by agreement only) |
|  | Sunday | Closed (or open by agreement only) |
|  | If there is no agreement to weekend working and this becomes necessary for reasons which are the responsibility of the Sub-Contractor, then any additional costs incurred by Ogilvie will be advised to and recovered from the Sub-Contractor’s account. In addition to the hours noted above the Principal Contract may restrict working hours. The Sub-Contractor is deemed to have made due allowance for these restrictions within the agreed programme. |  |
| 5.2 | Working restrictions including Principal Contract & site-specific restrictions: |  |
|  | Any other requirements the Project Manager deems necessary to ensure reduced disruption to surrounding businesses and residential residents. Given the location of the site no unloading anywhere other than inside the site boundary. |  |
| 5.3 | Sub-Contractor’s programme |  |
|  | Sub-Contractor to provide detailed programme of his works taking account of Ogilvie requirements and the dates agreed during this meeting. This programme must be issued in advance of the Sub-Contractor commencing works on site. Failure to submit a Sub-Contract Programme, in accordance with above, shall result in a deduction of £1,000 from the Sub-Contract account. |  |
| 5.4 | Progress meetings |  |
|  | The Sub-Contractor’s manager (and supervisor if deemed required) will be required to attend weekly / fortnightly progress meetings to assess current progress and short-term programme dates etc. Attendees to such meeting should be empowered to make decisions on behalf of the Sub-Contractor. |  |

| 6. Health & Safety |  |  |
| --- | --- | --- |
| 6.1 | Please refer to Ogilvie “Sub-Contractor Competence Assessment” and Construction Phase Plan documents for our General Health & Safety Conditions |  |
| 6.2 | Any operators of plant must be in possession of appropriate CITB/CPCS/NPORS certification (or equivalent industry standard). All other persons must have a valid CSCS/Skill card (or equivalent industry standard). |  |
| 6.3 | All labour on site will be required to wear safety helmets, safety boots, high visibility vests/jackets and glove protection. This will be strictly enforced. The Sub-Contractor should provide and ensure that operatives arrive with appropriate PPE for the task. Ogilvie shall charge for all PPE if issued to a Sub-Contractor and / or refuse access to site. An administration charge of £50 will apply to each instance of issued individual items of PPE, in additional to the cost of the PPE. |  |
| 6.4 | The Sub-Contractor must submit suitable risk assessments/ method statements (RA/MS) covering their proposed work activities at least 2 weeks in advance of site commencement to enable Ogilvie evaluation to be carried out. The Sub- Contactor must appoint a site based nominated person/ supervisor who will be required to monitor and ensure H&S compliance of the Sub-Contractor workforce and activities. |  |
| 6.5 | The Sub-Contractor’s site manager/supervisor must be in possession of all method statements and risk assessments. Details must be relayed to all the Sub-Contractors employees and provide a confirmation notice to Ogilvie in advance of the Sub-Contractor’s employees attending the Ogilvie site induction. |  |
| 6.6 | A safety induction will be carried out with all Sub-Contractor employees on site. Inductions shall not be carried out on an ongoing process as the site operatives arrive. Operatives should arrive on site before 8.30am to receive their induction and be in possession of a completed induction registration form and copies of their relevant training card/certification. Ogilvie reserve the right to amend the frequency of site inductions. Inductions will be carried out up to an agreed maximum number of employees. Any inductions more than this number will be charged at a cost of £75 per employee. |  |
|  | Agreed maximum number of employees to be inducted before charge applied | 10 |
| 6.7 | To comply with the Management of Health & Safety at Work Regulations, subcontractors must inform Site Management and obtain permission before any young persons are brought on site. Please refer to Ogilvie General Health & Safety Conditions relating to rules and procedures on young people on site. |  |
| 6.8 | Regular visits are made to site by Ogilvie Health & Safety Department and any non-conformance will be notified to the Sub-Contractor immediately for rectification. Sub-Contractors must attend any Health & Safety meetings convened on site at no charge to Ogilvie. Ogilvie must receive a copy of any inspection / audits carried out by the Sub-Contractor’s H&S representative, with any immediate actions being notified on the day. |  |
| 6.9 | Ogilvie reserves the right to remove individuals from site for breaching Health and Safety Regulations and Ogilvie rules and policies. |  |
| 6.10 | Ogilvie operates a Clean Floor Policy therefore all subcontractors are required to clear their debris daily, or more frequently to maintain a safe working environment. Failure to do so will result in Ogilvie employing others to clear up and recover the costs accordingly. |  |
| 6.11 | Ogilvie will expect all operatives attending site to provide details of their National Insurance (NI) number. Failure to do so will prevent such persons from starting work on site and their Employer will be required to provide written confirmation that they have a legal right to work in the UK, before they are allowed to start work on site. |  |
| 6.12 | Ogilvie require street works certificates, for any Sub-Contract works involving this type of work. |  |

| 7. Quality & customer service |  |
| --- | --- |
| 7.1 | Description of agreed Sub-Contract quality control, inspection, and handover procedures |
|  | Inspection & Test Plan The Sub-Contractor must produce and issue to Ogilvie, an Inspection & Test Plan (ITP) for their works in advance of site commencement. The ITP must be presented to the Ogilvie manager responsible for the Sub-Contract works package and we discussed/agreed. Should the Sub-Contactor not have their own ITP format, Ogilvie can assist. In-Process Checklists In addition, this ITP must identify the ‘in-process’ checklists that shall be used for their various element of work. These must be produced and submitted to Ogilvie before each of the work elements are commenced. These checklists must be completed as the works progress as ‘live’ documents and be submitted to Ogilvie as part of the Sub-Contractor Progress Reports, to evidence they are being carried out. Evidence of quality compliance should also be in the form of photographs, not just text. A full suite of these must be provided at the end of the Sub-Contract works (in one document, as part of the Sub-Contractor handover pack of information). It is the Sub-Contractors responsibility to liaise with other Sub-Contractors managers/supervisors on the project for interfaces between handing over elements of the works to each other, including any inspections and signatures required. Checklists should also identify where Ogilvie, or design Team members are required to inspect the works. The Sub-Contractor must advise who shall be responsible for the implementation and control of the ITP and in-process checklists, prior to commencement on site, or, at latest, when submitting progress Report No 1, or in Progress Meeting No 1. Failure to provide an ITP, in advance of the works commencing, shall result in a deduction of £1,000 from the Sub-Contractor account. Failure to carry out and provide in-process checklists, which is not acceptable, shall result in ‘no further payment’ of works, until all in-process checklists are in place and being utilised as intended. |
| 7.2 | Description of agreed Sub-Contract defects, snagging and maintenance procedures |
|  | Non-conformances notified must be rectified in a period to avoid any delay to the project works. Snagging must be completed within the period defined within the issued Snagmaster item. Making good defects items must be rectified within the timescales defined in the main contract. Failure to comply with these timescales shall result in the deduction of any additional costs incurred by OCL, from the Sub-Contract account. |
|  | Note: More specific Sub-Contract “response times” to be included in this section if available |
| 7.3 | Production of O&M manuals and required Ogilvie timescale |
|  | Final Draft O&M must be issued, with all supporting information, 4 weeks before the end of the Sub-Contract period, as identified in the Sub-Contract order. Final O&M must be provided, with all supporting information (including any certification), within 4 weeks of completion of the Sub-Contract works, or 4 weeks before the main contract completion date, whichever is the earliest. Failure to provide the Draft O&M information as identified above shall result in a deduction of 10% of the gross application of the subcontract works at that time. Failure to provide the Final O&M information as identified above shall result in no further payment, until released. |
| 7.4 | Description as to how the Sub-Contractor will protect their Works |
|  | Suitable protection must be provided to protect the Sub-Contact works, during the Sub-Contractors period on site and from any adjacent works. The Sub-Contractor should co-ordinate these requirements with other Sub-Contractors present on site at the time of their works. The Sub-Contractor shall remove this protection at their own cost, including disposal, as and when directed by Ogilvie. |
| 7.5 | Contractual Practical Completion |
|  | Ensure the subcontractor understands the aim and practical measurement of Contractual Practical Completion (or Sectional Completion / Partial Possession / or Similar) and their obligations supporting it. |
|  | Completion of works by the Sub-Contractor, acceptance and signed over to Ogilvie, then upon full issue of all O&M and completion documents. |
| 7.6 | If Quality Assurance in-process documentation is not maintained, up to date, and evidenced to Ogilvie we reserve the right to deduct, up to a maximum of 10% of the gross Sub-Contract application, until this is provided to the satisfaction of Ogilvie. |

| 8. Materials |  |  |  |
| --- | --- | --- | --- |
| 8.1 | Procurement |  |  |
|  | The Sub-Contractor advised checking procurement on perforated cladding, all other cladding no concern. The Sub-Contractor is to provide a Materials Procurement Schedule which must be not less than 2 weeks in advance of commencement on site. The Sub-Contractor agrees to provide Ogilvie with copies of all material and plant purchase orders (excluding commercially sensitive data) to confirm whether orders have been placed. Failure to provide the above information, within 7 days of request, shall result in a deduction of £1,000 from the Sub-Contract account. |  |  |
| 8.2 | Delivery of materials (time / access restrictions / delivery periods etc) |  |  |
|  | Deliveries to site must be scheduled and submitted to Ogilvie for approval. Due to the site’s location allowances must be included for access to the site. Due to lack of loading areas the site has adopted a “just in time” delivery policy to keep disruption to a minimum. |  |  |
| 8.3 | Agreed wastage on materials supplied by Ogilvie for use by the Sub-Contractor |  |  |
|  | Material description | Wastage (%) | Comments |
|  | N/A | % |  |
|  |  | % |  |
|  |  | % |  |
|  |  | % |  |
|  |  | % |  |
|  |  | % |  |
|  | The Sub-Contractor shall be responsible for any costs incurred because of exceeding these wastage percentages. The Sub-Contractor shall be responsible, unless proving sufficient notice to Ogilvie to supply additional materials, any costs incurred because of a lack of materials, through exceeding the waste percentages as identified above. |  |  |
| 8.4 | Project-specific policy regarding the use of Ogilvie waste skips |  |  |
|  | Skips will be present. All endeavours must be taken to reduce the volume of waste going into skips. Delivery packaging, pallets etc should be removed off site and is the responsibility of the Sub-Contractor. |  |  |

| 9. Information required: Upload to ASITE, or as directed otherwise by Ogilvie |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Item | Yes | No |  | Comments |  |
|  | - Full design drawings |  |  |  |  |  |
|  | - Fabrication drawings |  |  |  |  |  |
|  | - Working drawings |  |  |  |  |  |
|  | - Builder’s work details |  |  |  |  |  |
|  | - As built drawings (also copied onto disk) |  |  |  |  |  |
|  | - Warranties |  |  |  |  |  |
|  | - Method statement (project specific) |  |  |  | 2 weeks before site start |  |
|  | - Risk assessment |  |  |  | 2 weeks before site start |  |
|  | - Safety policy |  |  |  | 2 weeks before site start |  |
|  | - Detailed subcontract programme |  |  |  | 2 weeks before site start |  |
|  | - Quality control procedures |  |  |  | 2 weeks before site start |  |
|  | - COSHH assessment |  |  |  | 2 weeks before site start |  |
|  | - Statement of resource |  |  |  | 2 weeks before site start |  |
|  | - Material procurement schedule |  |  |  | 2 weeks before site start |  |
|  | - Performance bond |  |  |  |  |  |
|  | - Product guarantees |  |  |  | 2 weeks before site start |  |
|  | - Environmental policy & project plan |  |  |  |  |  |
|  | - Quality policy & project plan |  |  |  |  |  |
|  | - Training Plan |  |  |  |  |  |
|  | - Environment Assessment (e.g. BREEAM, compliance (project specific.) |  |  |  |  |  |
|  | - Others (state below) |  |  |  |  |  |
|  | Design CPD information and timescales |  |  |  |  |  |
| 9.2 | Information required by the Sub-Contractor |  |  | Required by |  |  |
|  | Specs Provided from architect |  |  |  |  |  |
|  | Any other information to be submitted as design progresses |  |  | - |  |  |
|  | SER Input Required? |  |  |  |  | no |
|  | Where the sub-contractor has a contractor design component which relates to the Technical Standards and falls within the Certification of Structural Design (SER) the necessary information must be issued timeously to enable the Certifying Engineer to sign off the design has been received. Ogilvie reserve the right to withhold payment if this information is not issued & received to meet the requirements of the main contract. |  |  |  |  |  |

| 10. Any Other Business / Schedule of Supporting Documents issued at meeting |  |
| --- | --- |
|  | Ogilvie require collaborative working throughout the sub-contract. |
|  | Ogilvie utilise Asite as the project Common Data Environment (CDE) and project Document Management & Collaboration system. The Sub-contractor must work to Ogilvie document management procedures at all times. |
|  | No social media publications or any kind are permitted by the Sub-Contractor unless permission has been obtained by Ogilvie in advance (by the Project Manager). |

The previous pages and details accurately record our discussions within this meeting, the Sub-Contractors obligations, and shall form part of the Sub-Contract order.

| OGILVIE (Ogilvie Construction Limited) |  |  |
| --- | --- | --- |
| Name | Signed | Date |
| Name | Signed | Date |

| Sub-Contractor |  |  |
| --- | --- | --- |
| Name | Signed | Date |
| Name | Signed | Date |